## Cover page
WORKING DOCUMENT
Task Group Management (TG-M 21-2)
2021-03-09
Agenda Item: | 4. Implementation of the Leeuwarden Declaration
Subject: | TG-M work plan 2021-22
Document No.: | TG-M 21/2 TG-M work plan
Date: | 2021-02-24
Submitted by: | CWSS
This document contains a draft work plan for TG-M 2021/22 which is based on the CWSS work plan submitted to WSB 32 (WSB 32/7 Annual workplan by CWSS).
Proposal: | Discuss and agree on work plan and deliverables

## TG-M work plan (2)
TG-M Workplan 21-22 (v.February 2021)
Table: Work plan 2021/22 of the Task Group Management (TG-M) with activities/deliverables/products of the group´s responsibility in black, and supervision and coordination activities in grey. Items in brackets are temporary dealt with in TG-M but will need further allocation within the TWSC (e.g., Partnership Hub). The table is based on the CWSS work plan 2021/22 as submitted to WSB 32 (WSB 32/7 Annual workplan by CWSS). Oversee=Processes and products are followed and aligned to trilateral policy and coordinated where necessary.
Role TG-M | § LD (full text visible as comment) | Activities / Deliverables from approved TWSC WORKPLAN 2019-22 and additional products/events/projects | 2021 | 2022 | Planned activities/deliverables | Responsible at CWSS | Responsible group/person/body | Status
Support and contribute | 3 | Development draft SIMP | 2021 |  | Draft SIMP developed following agreed preliminary structure, including key topics. Overseen by TG-WH, in collaboration with TG-MA, TG-M, NG-ST, NG-E, EG-C | SL | TG-WH and see col. F | scheduled
Support and contribute | 3 | Draft SIMP development: consultation phase and pilot implementation | 2021 |  | Working phase with site-managers to finish the content of the SIMP, followed by endorsement of WSB and formal consultation phase with advisory boards | SL | TG-WH | scheduled
Support and contribute | 3 | Draft SIMP final review, update and edit |  | 2022 | Review SIMP including input from site managers and consultation phase, edit and layout | SL | TG-WH | scheduled
Support and contribute | 3 | Adoption: Final SIMP and submission to UNESCO |  | 2022 | Concise SIMP document with an overview of the management system and agreements to improve collaboration on the key topics and online microsite with complementary background information | SL | TG-WH | in progress
Observe | 5 | Arctic Cooperation | 2021 |  | WSFI Arctic report and workshop in Yamal, Russia | KM | WSFI SG | in progress
Observe | 5 | Specific sites flyway count | 2021 |  | Main sites along flyway will be counted | KM | WSFI SG | in progress
Observe | 5 | Capacity Building Project | 2021 |  | Capacity building of WH sites along EAF/training courses/application proposal for IKI project | KM | WSFI SG | in progress
Observe | 5 | Capacity Building Project | 2021 |  | Evaluation of the outcomes of previous capacity building activities | KM | WSFI SG | scheduled
Observe | 5 | Website/Microsite Flyway | 2021 |  | Finalize Microsite | KM | WSFI SG | in progress
Observe | 5 | Arctic Cooperation |  | 2022 | follow up on 2021 workshop | KM | WSFI SG | scheduled
Observe | 5 | Integral Flyway Assessment Report 2020 | 2021 |  | Flyway Assessment Report 2020 | KM | WSFI SG | scheduled
Observe | 5 | Capacity Building Project |  | 2022 | Capacity building of WH sites along EAF/training courses/supporting specific site | KM | WSFI SG | scheduled
Observe | 5 | Specific sites flyway count |  | 2022 | Main sites along flyway will be counted | KM | EG-MB/BB | scheduled
Oversee | 12 | Breeding bird trend report |  | 2022 | Trend and status breeding birds up to 2019 | KM | EG-MB/BB | scheduled
Oversee | 12 | Migratory bird trend report | 2021 |  | Report on status trends of migratory birds | KM | EG-MB/BB | scheduled
Oversee | 12 | Workshop on protection of habitats and zoning rules; management guidelines | 2021 |  | Joint workshops between JMBB/JMMB and EG saltmarshes and dunes, report | KM | EG-MB/BB | scheduled
Oversee | 12 | Breeding success report | 2021 |  | Updated report on the rbeeding success of selected bird species in the Wadden sea up to 2019 | KM | EG-MB/BB | scheduled
Oversee | 12 | Evaluation and update of BB Action Plan | 2021 |  | Assessment of changes in the breeding bird cycle, determine differences in monitoring methods | KM | EG-MB/BB | in progress
Oversee | 12 | Adaption of update of BB Action Plan |  | 2022 | New guidelines for breeding bird monitoring | KM | EG-MB/BB | scheduled
Observe/support | 13 | ToR and work programme for EG Fish | 2021 |  | ToR | JB | WG-Sw. | completed
Oversee | 13 | Website/Microsite SWIMWAY | 2021 |  | Assignment external coordinator / funding stragtey / common project proposal / workshops | JB | EG-Sw. | in progress
Oversee | 13 | Recommendation for operational fish monitoring programme(s) under TMAP | 2021 |  | Workshops | JB | EG-Sw. | in progress
Oversee | 13 | Progress towards reaching the trilateral fish targets |  | 2022 | Funding stragtey / common project proposal / workshops | JB | EG-Sw. | scheduled
Oversee | 13 | QSR thematic report fish | 2021 |  | QSR thematic report fish | JB | EG-Sw. | in progress
Oversee | 13 | Communication platform |  | 2022 | Funding stragtey / common project proposal / workshops | JB | EG-Sw. | scheduled
Oversee | 13 | Activity plan for implementation of Swimway Vision and Action Programme | 2021 |  | Assignment external coordinator / funding stragtey / common project proposal / workshops | JB | EG-Sw. | scheduled
Responsible/ support | 14 | Management Workshop | 2021 |  | Managers workshops in the framwork of the SIMP in the working phase with site managers | SL | Parties in the three countries and Federal States, CWSS, TG-WH, TG-M | scheduled | Added: "support" in column A
Responsible | 14 | Wardening Workshop | 2021 |  | Workshop | JB | TG-M/NL | scheduled
Evaluate and support | 15 | SMP evaluation an update | 2021 |  | Evaluation of SMP | KM | EG-Seals | scheduled | Upon approval: EG-MM
Evaluate and support | 15 | Adoption of updated SMP |  | 2022 | final SMP 2022-20xx ready for being adopted | KM | EG-Seals | scheduled
Oversee | 15 | Harbour seal workshop | 2021 |  | Workshop | KM | EG-Seals | scheduled
16 | 16 | Harbour porpoise workshop II (WS Marine Mammals) | 2021 |  | Workshop | KM | EG-Seals | in progress
17 | 17 | Platform Alien Species | 2021 |  | Development and Installation of Internet Information Platform /TMAP Integration | SK | EG-Seals | in progress
Support | 20 | QSR MC Report | 2021 |  | TMAP report for MC | SK | EG-Seals | scheduled
Responsible for relevant themes | 20 | QSR Thematic Reports updates | 2021 |  | QSR Theamtic Report updates | SK | TG-MA | in progress
Responsible for relevant themes | 20 | QSR Thematic Reports updates |  | 2022 | QSR Theamtic Report updates | SK | TG-MA | in progress
Responsible | 21 | SIMP chapter on sustainable fisheries | 2021 |  | Inventory SIMP in QSR thematic reoprt fish | JB | TG-M, CWSS, consultant, in synergy with SIMP development and QSR Thematic Report Fisheries | in progress
Responsible | 21 | SIMP chapter on sustainable fisheries | 2021 |  | Common ground and legal framework on fisheries. Input from assessment of framework for sustainable fisheries, 2021 QSR and site-managers, 2022 agreements on sustainable fisheries. | JB | TG-M, CWSS, consultant, in synergy with SIMP development and QSR Thematic Report Fisheries | scheduled
Responsible | 21 | Status & "Recommendations" (term tbd) for principles of Framework Sustainable Fisheries | 2021 |  | Common ground and legal framework on fisheries. Assessment of framework for sustainable fisheries, input from 2021 QSR and site-managers, 2022 agreements on sustainable fisheries. | JB | TG-M | in progress
| 22 | All activities under LD 23 | 2021 |  | All activities under LD 23. | JB | TG-M | scheduled
| 22 | All activities under LD 23 |  | 2022 | All activities under LD 23. | JB | TG-M | scheduled
Responsible | 23 | Inventory or workshop | 2021 |  | Inventory and/or workshop | JB | TG-M | completed
Responsible | 23 | Inventory or workshop | 2021 |  | Recommendations to the TWSC for improving focussed and targeted collaboration and coordination | JB | TG-M | in progress
Responsible | 29 | Treated in SIMP as key topic (Overview on concepts for renewable energy transport/sea floor /(Inventory study 2020) | 2021 |  | Renewable energy is one of the key topics in the SIMP. Reports in synergy with QSR Thematic Report Energy | SL | TG-M, CWSS, consultant, in synergy with SIMP development and QSR Thematic Report Energy | in progress
Support | 32 | Support to the WSF Round table approach planned end 2020 (WSF on lead with support of Ph admin unit, CWSS and TG-M) | 2021 |  | Shipping Round Table, contribution to SIMP key topic, address PSSA OP and the LS Advisory Council request | CN | WSF | scheduled
| 36 | Science & Research projects reflecting the four thematic lines of the TRA | 2021 |  | Support on initiation joint programme trilateral research, e.g. by project development and application for funding. Preparation for ISWSS late 2021 | BB | TPC | in progress
| 36 | Science & Research projects reflecting the four thematic lines of the TRA |  | 2022 | Support on initiation joint programme trilateral research, e.g. by project development and application for funding. Preparation for TGC 2022 | BB | TPC | scheduled
| 42 | Policy Assessment Report (PAR) | 2021 |  | Installment of Drafting Group and preparing 1st draft of the MD Wilhelmshaven 2022 | BB |  | in progress
| 43 | Establish MCD Drafting Group | 2021 |  | preparing final draft of the MD Wilhelmshaven 2022 | BB |  | scheduled
| 43 | Draft MCD for national consultation | 2021 |  | Final draft of MD | BB |  | scheduled
| 43 | Trilateral Governmental Conference (TGC) |  | 2022 | Full Conference and Council meeting organised | BB |  | in progress
Support | 44 | International Scientific Wadden Sea Symposium (ISWSS) | 2021 |  | Postponed from March to November/December | SL | SH | scheduled
Supervise | N/A | Wadden Sea Plan | 2021 |  |  |  | [TG-M] | in progress | Not in CWSS work plan
Supervise | N/A | Wadden Sea Plan |  | 2022 |  |  | [TG-M] | in progress | Not in CWSS work plan
Note on B5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3. Develop a single integrated management plan for the entire transboundary World Heritage property
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3. Develop a single integrated management plan for the entire transboundary World Heritage property
Note on B7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3. Develop a single integrated management plan for the entire transboundary World Heritage property
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 3. Develop a single integrated management plan for the entire transboundary World Heritage property
Note on B9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5. Continue and further consolidate the work on the Flyway Vision in the framework of the Wadden Sea Flyway Initiative with the relevant governmental and non-governmental organisations and extend the cooperation in the context of the Wadden Sea Flyway Initiative, especially with regard to the Arctic, continue monitoring along the entire flyway, continue specific capacity building and increase the activation of partners
Note on B10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5. Continue and further consolidate the work on the Flyway Vision in the framework of the Wadden Sea Flyway Initiative with the relevant governmental and non-governmental organisations and extend the cooperation in the context of the Wadden Sea Flyway Initiative, especially with regard to the Arctic, continue monitoring along the entire flyway, continue specific capacity building and increase the activation of partners
Note on B11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5. Continue and further consolidate the work on the Flyway Vision in the framework of the Wadden Sea Flyway Initiative with the relevant governmental and non-governmental organisations and extend the cooperation in the context of the Wadden Sea Flyway Initiative, especially with regard to the Arctic, continue monitoring along the entire flyway, continue specific capacity building and increase the activation of partners
Note on B12: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5. Continue and further consolidate the work on the Flyway Vision in the framework of the Wadden Sea Flyway Initiative with the relevant governmental and non-governmental organisations and extend the cooperation in the context of the Wadden Sea Flyway Initiative, especially with regard to the Arctic, continue monitoring along the entire flyway, continue specific capacity building and increase the activation of partners
Note on B13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5. Continue and further consolidate the work on the Flyway Vision in the framework of the Wadden Sea Flyway Initiative with the relevant governmental and non-governmental organisations and extend the cooperation in the context of the Wadden Sea Flyway Initiative, especially with regard to the Arctic, continue monitoring along the entire flyway, continue specific capacity building and increase the activation of partners
Note on B14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5. Continue and further consolidate the work on the Flyway Vision in the framework of the Wadden Sea Flyway Initiative with the relevant governmental and non-governmental organisations and extend the cooperation in the context of the Wadden Sea Flyway Initiative, especially with regard to the Arctic, continue monitoring along the entire flyway, continue specific capacity building and increase the activation of partners
Note on B15: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5. Continue and further consolidate the work on the Flyway Vision in the framework of the Wadden Sea Flyway Initiative with the relevant governmental and non-governmental organisations and extend the cooperation in the context of the Wadden Sea Flyway Initiative, especially with regard to the Arctic, continue monitoring along the entire flyway, continue specific capacity building and increase the activation of partners
Note on B16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5. Continue and further consolidate the work on the Flyway Vision in the framework of the Wadden Sea Flyway Initiative with the relevant governmental and non-governmental organisations and extend the cooperation in the context of the Wadden Sea Flyway Initiative, especially with regard to the Arctic, continue monitoring along the entire flyway, continue specific capacity building and increase the activation of partners
Note on B17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 5. Continue and further consolidate the work on the Flyway Vision in the framework of the Wadden Sea Flyway Initiative with the relevant governmental and non-governmental organisations and extend the cooperation in the context of the Wadden Sea Flyway Initiative, especially with regard to the Arctic, continue monitoring along the entire flyway, continue specific capacity building and increase the activation of partners
Note on B18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12. Oversee the further implementation of the Action Plan for Breeding Birds and support an exchange of experiences of national and regional activities, including a potential further development, and undertake an evaluation in time for the next Trilateral Governmental Conference
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12. Oversee the further implementation of the Action Plan for Breeding Birds and support an exchange of experiences of national and regional activities, including a potential further development, and undertake an evaluation in time for the next Trilateral Governmental Conference
Note on B20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12. Oversee the further implementation of the Action Plan for Breeding Birds and support an exchange of experiences of national and regional activities, including a potential further development, and undertake an evaluation in time for the next Trilateral Governmental Conference
Note on B21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12. Oversee the further implementation of the Action Plan for Breeding Birds and support an exchange of experiences of national and regional activities, including a potential further development, and undertake an evaluation in time for the next Trilateral Governmental Conference
Note on B22: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12. Oversee the further implementation of the Action Plan for Breeding Birds and support an exchange of experiences of national and regional activities, including a potential further development, and undertake an evaluation in time for the next Trilateral Governmental Conference
Note on B23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 12. Oversee the further implementation of the Action Plan for Breeding Birds and support an exchange of experiences of national and regional activities, including a potential further development, and undertake an evaluation in time for the next Trilateral Governmental Conference
Note on B24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 13. Further develop and contribute to implementing the SWIMWAY Vision as an integrated approach to achieving the Trilateral Fish Targets by investigating, monitoring, managing and communicating topics concerning the ecology of fish of the Wadden Sea Area
Note on B25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 13. Further develop and contribute to implementing the SWIMWAY Vision as an integrated approach to achieving the Trilateral Fish Targets by investigating, monitoring, managing and communicating topics concerning the ecology of fish of the Wadden Sea Area
Note on B26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 13. Further develop and contribute to implementing the SWIMWAY Vision as an integrated approach to achieving the Trilateral Fish Targets by investigating, monitoring, managing and communicating topics concerning the ecology of fish of the Wadden Sea Area
Note on B27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 13. Further develop and contribute to implementing the SWIMWAY Vision as an integrated approach to achieving the Trilateral Fish Targets by investigating, monitoring, managing and communicating topics concerning the ecology of fish of the Wadden Sea Area
Note on B28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 13. Further develop and contribute to implementing the SWIMWAY Vision as an integrated approach to achieving the Trilateral Fish Targets by investigating, monitoring, managing and communicating topics concerning the ecology of fish of the Wadden Sea Area
Note on B29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 13. Further develop and contribute to implementing the SWIMWAY Vision as an integrated approach to achieving the Trilateral Fish Targets by investigating, monitoring, managing and communicating topics concerning the ecology of fish of the Wadden Sea Area
Note on B30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 13. Further develop and contribute to implementing the SWIMWAY Vision as an integrated approach to achieving the Trilateral Fish Targets by investigating, monitoring, managing and communicating topics concerning the ecology of fish of the Wadden Sea Area
Note on B31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 14. Work intensively on cooperation at the operational management level and secure adequate wardening and management across the whole Wadden Sea Area
Note on B32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 14. Work intensively on cooperation at the operational management level and secure adequate wardening and management across the whole Wadden Sea Area
Note on B33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 15. Reaffirm the rules on taking and releasing of seals in accordance with Article IV of the Agreement on the Conservation of Seals in the Wadden Sea and adopt the updated Seal Management Plan 2018-2022, which also takes into account the management of grey seals
Note on B34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 15. Reaffirm the rules on taking and releasing of seals in accordance with Article IV of the Agreement on the Conservation of Seals in the Wadden Sea and adopt the updated Seal Management Plan 2018-2022, which also takes into account the management of grey seals
Note on B35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 15. Reaffirm the rules on taking and releasing of seals in accordance with Article IV of the Agreement on the Conservation of Seals in the Wadden Sea and adopt the updated Seal Management Plan 2018-2022, which also takes into account the management of grey seals
Note on B36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 16. duly take account of the fact that harbour porpoises are present in the Wadden Sea
Note on B37: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 17. Undertake further steps towards a Trilateral Management and Action Plan Alien Species (MAPAS), which should include relevant steps for public awareness and cooperation on early warning and measures, integrating a related monitoring programme, based on the national data underpinning the Trilateral Assessment and Monitoring Programme, including the installation of the network platform at the Common Wadden Sea Secretariat
Note on B38: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 20. Produce updates of the online Wadden Sea Quality Status Report and deliver a comprehensive synthesis report in time for the next Trilateral Governmental Conference
Note on B39: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 20. Produce updates of the online Wadden Sea Quality Status Report and deliver a comprehensive synthesis report in time for the next Trilateral Governmental Conference
Note on B40: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 20. Produce updates of the online Wadden Sea Quality Status Report and deliver a comprehensive synthesis report in time for the next Trilateral Governmental Conference
Note on B41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 21. Further develop steps for the sustainability of fisheries in the Wadden Sea Area on the trilateral level, in close cooperation with responsible authorities and relevant stakeholders and initiatives (e.g. certification procedures), within the Framework for Sustainable Fisheries, taking into account both the importance of the ecosystem service of providing regional sea food in this respect and the integrity of the World Heritage Site
Note on B42: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 21. Further develop steps for the sustainability of fisheries in the Wadden Sea Area on the trilateral level, in close cooperation with responsible authorities and relevant stakeholders and initiatives (e.g. certification procedures), within the Framework for Sustainable Fisheries, taking into account both the importance of the ecosystem service of providing regional sea food in this respect and the integrity of the World Heritage Site
Note on B43: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 21. Further develop steps for the sustainability of fisheries in the Wadden Sea Area on the trilateral level, in close cooperation with responsible authorities and relevant stakeholders and initiatives (e.g. certification procedures), within the Framework for Sustainable Fisheries, taking into account both the importance of the ecosystem service of providing regional sea food in this respect and the integrity of the World Heritage Site
Note on B44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22. Substantially reduce the amount of marine litter in the Wadden Sea by the year 2030
Note on B45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 22. Substantially reduce the amount of marine litter in the Wadden Sea by the year 2030
Note on B46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 23. Make use of all relevant existing monitoring and action programmes, as well as existing action plans, to gain and exchange adequate additional knowledge on sources and impacts of marine litter on the Wadden Sea ecosystem and stimulate and support appropriate measures
Note on B47: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 23. Make use of all relevant existing monitoring and action programmes, as well as existing action plans, to gain and exchange adequate additional knowledge on sources and impacts of marine litter on the Wadden Sea ecosystem and stimulate and support appropriate measures
Note on B48: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 29. Review and monitor the impacts of renewable energy production and energy transportation on the Wadden Sea ecosystem and consider measures to avoid or mitigate possible negative impacts by looking for best environmental practices also with the aim of developing, for example, related common principles to evaluate the impact of high-voltage power cables in the Wadden Sea Area in close consultation with the responsible bodies and stakeholders
Note on B49: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 32. Encourage the competent national shipping and nature conservation authorities to continue their dialogue in order to achieve an even higher level of safety and cooperation, inter alia by raising the general awareness and information level;
Note on B50: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36. continue to strengthen its cooperation with the scientific community by installing a trilateral programming committee in order to establish a joint programme on research issues relevant to the Wadden Sea World Heritage, taking into account the Trilateral Research Agenda and encourage the scientific community to develop a trilateral research platform and to promote pilot studies on nature restoration
Note on B51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 36. continue to strengthen its cooperation with the scientific community by installing a trilateral programming committee in order to establish a joint programme on research issues relevant to the Wadden Sea World Heritage, taking into account the Trilateral Research Agenda and encourage the scientific community to develop a trilateral research platform and to promote pilot studies on nature restoration
Note on B52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 42. Review, in time for the next Trilateral Governmental conference, the progress made on the items described in the Declaration
Note on B53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 43. Hold the next Trilateral Governmental Conference on the Protection of the Wadden Sea and the 14th Trilateral Wadden Sea Governmental Council meeting in 2022
Note on B54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 43. Hold the next Trilateral Governmental Conference on the Protection of the Wadden Sea and the 14th Trilateral Wadden Sea Governmental Council meeting in 2022
Note on B55: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 43. Hold the next Trilateral Governmental Conference on the Protection of the Wadden Sea and the 14th Trilateral Wadden Sea Governmental Council meeting in 2022
Note on B56: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 44. Hold the 15th International Scientific Wadden Sea Symposium in Germany prior to the 14th Trilateral Wadden Sea Governmental Council